## Sponsor Inputs
# | High level ideas / Features
1 | Create Account
2 | View Restaurants
3 | Search Restaurants
4 | View Menu
5 | Add to Cart
6 | Purchase
7 | Restaurant views order
8 | Restaurant marks order as delivered
Notes:
1 | The above points were listed as draft ideas by the project sponsor.
2 | The project sponsor mentioned that he wants to compete against Talabat.
3 | As a sponsor, I am planning to compete against Talabat.
4 | This is a view only file, you can make a copy then edit in the copy.
5 | You can find a tab named Product Backlog Template, please feel free to use it when creating your product backlog.

## Product Backlog Template
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
As a < type of user >, I want < some goal > so that < some reason >
| Create Account | As a developer, I want each user to have an account, so that his address and information are stored. | 5 |  | 1
| View Restaurants | As a customer, I want to see which restaurants are available on the app, so that I can choose the restaurant. | 3 |  | 2
| Search Restaurants | As a customer, I want to search for a specific restaurant, so that I can order my prefered food. | 5 |  | 3
| View Menu | As a customer, I want to view the menu, so that I can see the options to order from. | 5 |  | 4
| Add to Cart | As a customer, I want a cart, so that I can collect different items to buy at once. | 5 |  | 5
| Purchase | As a developer, I want to provide the customer with different purchasing options, so that the customer chooses his payment method. | 5 |  | 6
| Restaurant views order | As a restaurant, I want to view the order, so that I can prepare and check for any comments from the customer. | 5 |  | 7
| Restaurant marks order as delivered | As a restaurant, I want to mark the order's status, so that order progress can be tracked. | 3 |  | 8